## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2023 - <Data Analytics> Project Schedule
|  | PROJECT START DATE | 2023-07-01
|  | Display Week Sr No | 1 | [10 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24 | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2023-06-26 to 2023-08-27
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-06-26 to 2023-08-27
1 | [Initiation]
1.1 |  | Requirement gathering |  |  |  | Chetna | 2023-08-01 | 2023-08-04 | 2023-08-04 | 3 | Completed
2 | [Planning]
|  | Finalizing the method |  |  |  | Chetna | 2023-08-11 | 2023-08-13 | 2023-08-13 | 2 | Completed
| 3 Designing |  |  |  |  | Chetna | 2023-08-12 | 2023-08-13 | 2023-08-13 | 6 | Completed
| 4 Development |  |  |  |  | Chetna | 2023-08-12 | 2023-08-14 | 2023-08-14 | 5 | Completed
| 5 Testing |  |  |  |  | Chetna | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2 | Completed
| 6 Deployment |  |  |  |  | Chetna | 2023-08-14 | 2023-08-15 | 2023-08-15 | 3 | Completed
| 7 Closure |  |  |  |  | Chetna | 2023-08-14 | 2023-08-15 | 2023-08-15 | 1 | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Analysis of student intern |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Resume maker
PROJECT SCOPE | Students will get an idea of what should be added in each section of the resume.
PROJECT START DATE | 2023-07-01
PROJECT END DATE | 2023-09-15
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1Requirement gathering | Chetna | 2023-08-01 | 2023-08-04 | 3 | COMPLETED
| 2 Planning | Chetna | 2023-08-11 | 2023-08-13 | 2 | COMPLETED
| 3 Designing | Chetna | 2023-08-12 | 2023-08-13 | 1 | COMPLETED
| 4 Development | Chetna | 2023-08-12 | 2023-08-14 | 2 | COMPLETED
| 5 Testing | Chetna | 2023-08-14 | 2023-08-15 | 1 | COMPLETED
| 6 Deployment | Chetna | 2023-08-14 | 2023-08-15 | 1 | COMPLETED
| 7 Closure | Chetna | 2023-08-14 | 2023-08-15 | 1 | COMPLETED